2004 CCSC Northwest Conference Timeline

(Revised: Oct 15, 2003)

Conference:
Friday October 8 and Saturday October 9, 2004

Willamette University, Salem, Oregon

Timeline

10/01/03
2004 “Preliminary Call for Papers” sent to Central Washington University for Inclusion in the 2003 Conference Packet

10/01/03
List of  2003 Student Poster Presenters sent to Central Washington University for Inclusion in the 2003 Conference Packet

10/01/03
2004 "Call for Student Posters" sent to Central Washington University for Inclusion in the 2003 Conference Packet

10/04/03
Regional Board Meeting and 2004 Conference Committee Meeting Following 2003 Conference Wrap-up (Saturday)

11/03/03
Mail and email “First Call for Papers”

01/12/04
Mail and email “Last Call for Papers”

01/24/04
Regional Board Meeting at Willamette University (Saturday)

03/12/04
Deadline for Paper Submissions

03/15/04
Papers to Referees

03/26/04
Deadline for Tutorial and Panel Discussion Submissions

04/16/04
Deadline for Paper Reviews Returned to Paper Chair

05/01/04
Program Meeting at Willamette University – Program Set 

05/07/04
Reviews Returned to Authors, Notification of Acceptance

05/07/04
Notification of Tutorial and Panel Discussion Acceptance

05/15/04
Regional Board Meeting at University of Washington, Bothell (Saturday)

06/04/04
Deadline for Final Drafts of Papers

06/11/04
Papers to Consortium Editor

08/20/04
Mail Conference Announcement and Registration Materials

08/20/04
E-mail Conference Announcement and Registration Materials

09/24/04
Deadline for Student Poster Abstract Submissions

10/04/04
2005 “Preliminary Call for Papers” sent to Willamette University for Inclusion in 2004 Conference Packet

10/04/04
List of 2004 Student Poster Presenters sent to Willamette University for Inclusion in the 2004 Conference Packet

10/04/03
2005 "Call for Student Posters" sent to Willamette University for Inclusion in the 2004 Conference Packet

10/08/04
2004 Conference Registration Begins at Noon

10/09/04
Regional Board Meeting and 2005 Conference Committee Meeting Following 2004 Conference Wrap-up (Saturday)

