# 2008 CCSC Northwest Conference Timeline

# Conference Date:	October 10 & 11, 2008

# SOU, Ashland, OR

## Timeline
Updated 3/5/2008

Date					  Activity

10/08/2007	2008 “Preliminary Call for Papers and Student Posters” sent to Southern Oregon University for Inclusion in the 2007 Conference Packet

10/13/2007	Regional Board Meeting and 2008 Conference Committee Meeting Following 2007 Conference Wrap-up (Saturday)

10/23/2007	Drafts of 2008 documents emailed to Regional Board for Review

10/26/2007	Documents for Web Publication sent to Webmaster.

11/05/2007	Mail and email “First Call for Papers”

01/12/2008	Mail and email “Last Call for Papers” and Update Website

01/26/2008	Regional Board Meeting, telephone conference, 10:00 a.m.

03/05/2008	(3/12/2008) Deadline for Paper Submissions

03/16/2008	(3/23/2008) Papers Emailed to Referees

03/19/2008	(3/26/2008) Deadline for Tutorial and Panel Discussion Submissions

04/16/2008	(4/23/2008) Deadline for Paper Reviews Returned to Paper Chair

04/19/2008	(4/26/2008) Program Meeting at SOU, Ashland, OR – Program Set

05/05/2008	Reviews Returned to Authors, Notification of Acceptance

05/05/2008	Notification of Tutorial and Panel Discussion Acceptance

05/17/2008	Regional Board Meeting at Pacific Lutheran University, Tacoma WA, 12:00-4:00 p.m.

06/09/2008	Deadline for Final Drafts of Papers

06/16/2008	(6/20/2008) Papers to Consortium Editor

08/20/2008	Mail and Email Conference Announcement and Registration Materials

09/27/2008	Deadline for Student Poster Abstract Submissions

10/05/2008	2008 “Preliminary Call for Papers and Student Posters” sent to SOU for Inclusion in 2008 Conference Packet

10/05/2008	List of 2008 Student Poster Presenters sent to SOU for Inclusion in the 2008 Conference Packet

10/10/2008	2008 Conference Registration Begins at Noon

10/11/2008	Regional Board Meeting and 2009 Conference Committee Meeting Following 2008 Conference Wrap-up (Saturday)

10/??/2007	Send Post Conference Information and Announcements.

Note: Dates are somewhat flexible and may be adjusted by the host institution.  However, none of the dates can be moved more than a week or so.